🍅

YIGIT COMPANY

DIGITAL TRANSFORMATION

ROADMAP

From Greenhouse to Global Market

Complete Value Chain Digitalization

Greenhouse → Harvest → Transport → Export → Contracts → Finance

| Parameter | Value |
| --- | --- |
| Document | YGT Digital Transformation Roadmap v4.0 |
| Date | March 2026 |
| Status | For Management Review & Approval |
| Classification | CONFIDENTIAL — Internal Only |
| Prepared By | Data Analytics Department |
| Based On | Analysis of 983 shipments, 461 invoices, 28 contracts, 24 export firms, 111 buyers + Transport TechSpec v1.0 + Greenhouse TechSpec v3.0 |
| Deliverables | 5 Projects × Full Technical Specification + UI/UX Prototype |
| Key Updates v4.0 | P1 Greenhouse expanded to 11-module platform (24–32 weeks). P2 Transport expanded to 4-module fleet system (20–26 weeks). Overall timeline: 18–24 months. |

# 1. EXECUTIVE SUMMARY

YGT Holding operates a vertically integrated tomato export business spanning greenhouse cultivation, international logistics, multi-firm export structures, and financial management. Currently, the entire operation runs on Excel spreadsheets, phone calls, and WhatsApp messages. This document presents a comprehensive plan to digitalize the complete value chain.

| SHIPMENTS ANALYZED | INVOICES ANALYZED | OUTSTANDING DEBT | EXCEL FILES TO REPLACE |
| --- | --- | --- | --- |
| 983 | 461 | $8.3M | 9 greenhouse + main ops |

## 1.1 Key Findings

| # | Finding | Impact | Project |
| --- | --- | --- | --- |
| 1 | 983 shipments tracked in Excel with 44 fields each | High error risk, no real-time visibility, 9 roles editing same file | P3 Export |
| 2 | $8.3M outstanding debt across 28 contracts (57% unpaid) | Cash flow crisis, firms cannot repay bank credits | P4 Contracts |
| 3 | 90 sales reports missing — trucks sold but no report filed | Revenue leakage, no accountability for sales reps | P3 Export |
| 4 | $10K rule — bimodal distribution proves systematic cash optimization | 35.6% invoices $5–8K (cash), 60.7% $15–20K (bank), 0% near $10K | P4 Contracts |
| 5 | 24 export firms with complex splitting (2-firm common, 3-firm rare) | 2 CMR documents per split truck, quota impact per firm | P4 Contracts |
| 6 | 9 Excel files with 20,000+ data points run the entire greenhouse | No single view, no mobile access, no alerts, no heatmaps, no cross-season comparison | P1 Greenhouse |
| 7 | 8 document types filled manually by Sirin/Aynur daily by 13:00 | 2–3 hours daily on manual template filling | P4 Documents |
| 8 | No unified dashboard — executives call departments for information | Delayed decision-making, no strategic visibility | P5 Finance |
| 9 | No fleet visibility — truck status, documents, maintenance all in Excel/phone | Border entry bans discovered at border, unknown trip profitability, fuel manipulation | P2 Transport |

## 1.2 Proposed Solution

5 interconnected projects covering the entire value chain, built on a unified Django+React platform with shared database. Total timeline: 18–24 months (revised to accommodate expanded P1 Greenhouse and P2 Transport scopes). Priority: Export Operations first (most pain, most data available).

| P1 GREENHOUSE | P2 TRANSPORT & FLEET | P3 EXPORT | P4 CONTRACTS | P5 FINANCE |
| --- | --- | --- | --- | --- |
| 11 Modules, 27 obs types 9 Excel files, 20K+ records Inta EVO integration | 4 Modules: Fleet, Drivers, Service, Trips 4 Roles, QR, GPS Traccar | 983 shipments 13 steps, 9 roles | 28 contracts $10K rule, 8 doc types | Logo Tiger, 1C Kredit, Dashboard |

# 2. CURRENT STATE ANALYSIS (AS-IS)

## 2.1 How the Business Operates Today

The tomato export operation follows a fixed seasonal cycle (September–March). Every day, management coordinates 15+ greenhouse blocks, 24 export firms, 111 import companies, 2,000+ trucks, and 9 operational roles using phone calls, WhatsApp, and Excel.

### The Daily Workflow (Manual)

| # | Time | Activity | Who | Tool Used |
| --- | --- | --- | --- | --- |
| 1 | 06:00 | Decide harvest blocks — which blocks to pick, how much kg | Gadam | Phone calls + memory |
| 2 | 07:00 | Loading — weigh tomatoes, load into truck, record weight | Soltanmyrat | Paper + WhatsApp photo |
| 3 | 08:00 | Decide destination — which country, city, customer, import firm | Gadam + Agamyrat | Phone discussion |
| 4 | 08:30 | Decide export firms — which 1–3 firms, split kg | Gadam + Agamyrat | Mental calculation |
| 5 | 09:00 | Prepare documents — CMR, invoice, customs, fito, CT-1 (8 types!) | Sirin / Aynur | Excel templates + manual fill |
| 6 | 10:00 | Customs clearance — submit documents to Turkmen customs | Sirin | Paper documents |
| 7 | 13:00 | DEADLINE — all documents must be ready | Sirin / Aynur | Deadline pressure |
| 8 | 14:00 | Truck departs — driver leaves toward border | Transport | Phone call notification |
| 9 | 1–7 days | In transit — no real-time tracking, rely on driver calls | Driver | Phone calls |
| 10 | Arrival | Sales — rep sells at destination, should submit report | Arap / Aganazar | WhatsApp / Phone |
| 11 | ??? | Report — 90 out of 461 reports are MISSING | Arap / Aganazar | Should use Excel, often don’t |

## 2.2 Current Systems Landscape

| System | Purpose | Status | Integration Plan |
| --- | --- | --- | --- |
| Excel (Main Export) | 983 shipments, 44 fields, 9 roles edit | Active — PRIMARY | Replace with P3 Export |
| Excel (Contracts) | 28 contracts, 461 invoices, 8 doc templates | Active | Replace with P4 Contracts |
| Excel (Greenhouse × 9) | 9 files: Monitoring, Tuta, Tabacci, Plant reg, Fruit wt, Fertilizer, Chemical, Temp, Irrigation. 20,000+ records, 7 seasons. | Active — CRITICAL | Replace with P1 Greenhouse (11 modules) |
| Excel (Fleet) | Truck/driver spreadsheets, no maintenance tracking | Active | Replace with P2 Fleet |
| Logo Tiger ERP | Formal accounting, tax reporting | Active (MSSQL) | READ integration in P5 |
| 1C Buhgalteriya | Credit/loan management, bank accounts per firm | Active (Russian) | Manual import → API later |
| Trip Management | Driver expenses, fuel costs (Django+React) | Active (internal) | REST API integration in P2 |
| Inta EVO Controllers | Greenhouse climate (temp) + irrigation automation. EVO-1 and EVO-2 with valve mapping. | Active — No digital link | Auto-import integration in P1 |
| WhatsApp Groups | Communication between all roles | Active — CRITICAL | Replace with in-app + Telegram |
| Phone Calls | Decision-making, status updates | Active — DAILY | Replace with dashboard + alerts |

## 2.3 Pain Points by Role

| Role | Person(s) | Biggest Pain Point | Digital Solution |
| --- | --- | --- | --- |
| Logist | Gadam, Agamyrat | No visibility into available harvest, trucks, firm quotas. | Dashboard with real-time data |
| Sklad | Soltanmyrat | Manual weight recording on paper. Photos via WhatsApp. | Mobile harvest input form |
| Document | Sirin, Aynur | Fill 4–8 Excel templates per truck DAILY by 13:00. | Auto-generate from shipment data |
| Transport | Malik, Haltac | No fleet visibility. Document expiry discovered at border. | Fleet dashboard + departure bans |
| Agronomist | ES team | Must open 9 separate Excel files for greenhouse status. No mobile access. Paper → Excel. No alerts or heatmaps. | P1: Single platform with 11 modules, mobile PWA, QR scanning, auto-alerts, heatmaps |
| Scout / Block Mgr | Field staff | Write pest counts on paper, enter into Excel later. No QR scanning despite QR labels on traps. | P1: Mobile app → scan QR → enter count → auto-sync |
| Dispatcher | — (new) | No trip P&L, no fuel norms, no driver scoring. | P2: Full dispatch dashboard |
| Technician | — (new) | No maintenance forecasting. Reactive repairs only. | P2: Service module + predictions |
| HR Manager | — (new) | Driver documents tracked manually. Visa expiry missed. | P2: Document control + auto-alerts |
| Sales Rep | Arap, Aganazar | No enforcement of sales report submission. | Mandatory report before closing |
| Management | Directors | Must call departments for information. | Executive dashboard + reports |

## 2.4 Data-Driven Insights from Excel Analysis

### 2.4.1 Shipment Volume & Seasonality (983 shipments)

| Month | Shipments | Tonnes | Revenue | Avg $/kg | Trend |
| --- | --- | --- | --- | --- | --- |
| Sep 2025 | 82 | 1,484 t | $1,291,080 | $0.87 | Season start |
| Oct 2025 | 124 | 2,245 t | $1,953,150 | $0.87 | ↑ +51% PEAK |
| Nov 2025 | 118 | 2,136 t | $1,858,320 | $0.87 | ↓ -5% |
| Dec 2025 | 68 | 1,231 t | $1,070,970 | $0.87 | ↓ -42% |
| Jan 2026 | 42 | 760 t | $661,200 | $0.87 | ↓ -38% |
| Feb 2026 | 27 | 489 t | $425,430 | $0.87 | Season end |
| TOTAL | 461 | 8,345 t | $7,260,150 | $0.87 | Full season |

### 2.4.2 The $10,000 Rule — Mathematical Proof

Analysis of 461 invoices reveals a bimodal distribution proving systematic financial engineering:

| Range | Invoices | % Total | Interpretation | Money Flow |
| --- | --- | --- | --- | --- |
| $0–$5,000 | 3 | 0.7% | Small orders | Cash |
| $5,000–$8,000 | 162 | 35.6% | SPLIT trucks (2 firms, each <$10K) | CASH |
| $9,000–$12,000 | 0 | 0.0% | DEAD ZONE — nobody near $10K | N/A |
| $15,000–$20,000 | 276 | 60.7% | FULL trucks (1 firm, >$10K) | BANK → credit |
| $20,000+ | 10 | 2.2% | Large orders | Bank |

### 2.4.3 Outstanding Debt by Firm

| Firm | Contracts | Contract $ | Exported $ | Paid $ | OWED $ | Paid % |
| --- | --- | --- | --- | --- | --- | --- |
| YGT | 5 | $2.83M | $1.32M | $1.13M | $1.70M | 40% |
| HMS | 4 | $2.27M | $1.23M | $1.06M | $1.21M | 47% |
| ISH | 2 | $1.07M | $995K | $66K | $1.00M | 6.6% |
| MA | 3 | $1.50M | $850K | $567K | $945K | 38% |
| DM | 3 | $1.50M | $1.20M | $594K | $918K | 40% |
| TOTAL | 28 | $14.6M | $5.88M | $6.34M | $8.3M | 43% |

### 2.4.4 Market Distribution

| Country | Invoices | Revenue | % of Revenue | Top Buyer |
| --- | --- | --- | --- | --- |
| 🇰🇿 Kazakhstan | 330 | $4,752,201 | 80.8% | Aranshy KZ (146), Nur-Alem (136) |
| 🇷🇺 Russia | 108 | $831,546 | 14.1% | SAH FRUT Moscow (54) |
| 🇺🇿 Uzbekistan | 11 | $206,906 | 3.5% | Mavlonoi Rumi (11) |
| 🏳️ Other | 12 | $86,637 | 1.5% | Various |

# 3. TARGET STATE VISION (TO-BE)

## 3.1 The Unified Platform

A single web application replacing all Excel files, phone calls, and WhatsApp coordination. Every role logs in, sees their dashboard, enters their data, and the entire value chain is connected in real-time.

| Capability | AS-IS (Today) | TO-BE (Platform) |
| --- | --- | --- |
| Greenhouse monitoring | Agronomist opens 9 Excel files. Paper notes in greenhouse. | Single dashboard: pest alerts, heatmaps, growth charts, irrigation status. Mobile PWA with QR scanning. |
| Pest scouting | Paper → Excel. No QR scan. No alerts. | Scan QR on trap → enter count → auto-sync. Heatmaps + threshold alerts. |
| Climate/irrigation data | Manually copy from Inta EVO controllers to Excel | Auto-import from Inta EVO. Real-time temp/irrigation dashboard. |
| Harvest availability | Gadam calls block managers | Dashboard: real-time kg per block, fruit weight trends |
| Export decision | Phone discussion: which firm, which country | System shows: available quota, $10K calculator, firm suggestions |
| Document preparation | Sirin fills 4–8 Excel templates (2–3 hours) | One click: auto-generate all documents from shipment data |
| Fleet management | Excel spreadsheets + phone calls | Fleet board: QR codes, status badges, departure ban checks, maintenance forecasts |
| In-transit tracking | Call driver: where are you? | GPS map (Traccar): real-time position, speed, ETA |
| Trip profitability | Revenue known, costs scattered | Per-trip P&L: revenue − all expenses = profit margin |
| Sales reporting | WhatsApp (or nothing) | Mandatory form: system blocks closing without report |
| Financial overview | Check Excel + Logo Tiger + 1C separately | Single dashboard: revenue, debt, profit by route, firm risk |

## 3.2 Expected Business Impact

| Impact Area | Current Cost | Expected Saving | How |
| --- | --- | --- | --- |
| Greenhouse data entry | Paper → 9 Excel files, delayed | Real-time mobile entry | PWA + QR scan + offline sync |
| Pest response time | Days (discover in Excel review) | Hours (auto-alerts) | Threshold alerts + heatmaps |
| Cross-data analysis | Impossible (9 separate files) | Automatic cross-module views | Temp + plant growth + irrigation linked |
| Document preparation | 2–3 hours/day × 2 people | 80% reduction (30 min/day) | Auto-generation from templates |
| Missing sales reports | 90 missing = unknown revenue | 0 missing (enforced) | System blocks close without report |
| Border incidents | Trucks stuck (expired docs) | Zero incidents | Document Control: auto departure ban |
| Fuel waste | 10–15% estimated | 10–15% savings | Per-100km norm tracking |
| Vehicle downtime | Unknown, reactive repairs | 30–50% reduction | Mileage-based maintenance forecasting |
| Decision speed | 30+ min per shipment | 5 min with data on screen | Dashboard + recommendations |
| Management visibility | Phone calls to departments | Self-serve dashboard | Executive analytics |

# 4. PROJECT PORTFOLIO (5 PROJECTS)

## 4.1 PROJECT 1: Yigit ES Greenhouse Platform

EXPANDED SCOPE — Based on Greenhouse Technical Task v3.0 11 Modules: Scouting · Plant Registration · Fruit Weight · Fertilizer · Chemical · Climate · Irrigation · Reporting · Administration · Harvest Recording · Weekly Harvest Planning Replaces 9 Excel files · 20,000+ data points · 7 seasons of history · Block A (4 greenhouses: A1–A4)

| Parameter | Value |
| --- | --- |
| Scope | Complete greenhouse management platform: pest scouting with QR scanning (27 observation types), plant growth measurements, fruit weight sampling, fertilizer tracking with stock management, pesticide catalog and application log, climate monitoring (Inta EVO auto-import), irrigation & drainage with complex calculations, reporting dashboard with heatmaps, full administration, daily harvest recording with mobile input and P3 export linkage, and weekly harvest planning grid with plan vs actual tracking. |
| Key output | Real-time answer to: WHAT IS THE GREENHOUSE STATUS? Pest pressure heatmaps, growth trends, climate data, irrigation efficiency, fertilizer consumption — all in one dashboard. NEW in v3.0: Real-time answer to HOW MUCH HARVEST IS AVAILABLE TODAY/THIS WEEK? with daily harvest recording, 7-day forecast, and weekly planning grid. Feeds harvest data to P2 Transport and P3 Export. |
| Current state | 9 separate Excel files with 20,000+ data points across 7 seasons (2018–2025). Paper-based field observations entered into Excel later. Inta EVO controller data manually copied. No mobile access, no alerts, no heatmaps. |
| Users | Administrator, Agronomist, Data Entry, Viewer, Block Manager — 5 roles with configurable permissions |
| Key integration | Inta EVO-1 and EVO-2 controllers (auto-import climate + irrigation data) + YGT shared platform (harvest data to P3 Export) |
| Estimated duration | 24–32 weeks in 11 internal phases (see detailed breakdown below) |
| Dependencies | None — can develop in parallel. Produces harvest availability data for P2, P3, P4, P5. |
| Technical Spec | Full specification available: Yigit_ES_Greenhouse_Technical_Task_v3.0 (separate document, 11 modules, expanded scope with harvest recording and weekly planning) |

### 4.1.1 Core Problems Solved

| # | Problem | Current State | Target State |
| --- | --- | --- | --- |
| 1 | No single view | Agronomist opens 9 Excel files | One dashboard with all greenhouse data |
| 2 | No mobile access | Paper notes, enter into Excel at office | PWA with offline sync + QR scanning |
| 3 | No real-time alerts | Discover pest pressure by reviewing Excel | Auto-alerts when thresholds exceeded |
| 4 | No heatmaps | Read hundreds of rows to find problems | Visual greenhouse map with color-coded pressure |
| 5 | No Inta integration | Manually copy temp/irrigation from controllers | Background auto-import from EVO-1 and EVO-2 |
| 6 | No cross-season comparison | Extremely difficult in Excel | Side-by-side season comparison for any metric |
| 7 | QR codes unused digitally | QR labels on traps/plants, only visual | Scan QR → identify trap/plant → enter data |
| 8 | No cross-module analysis | Temp, irrigation, growth in separate files | Linked weekly view: temp + growth + radiation |

### 4.1.2 Excel Files to Replace (9 files)

| Excel File | Records | Seasons | Key Challenge | Module |
| --- | --- | --- | --- | --- |
| A_Greenhouse_Monitoring | ~5,000+ | 2020–2025 | 27 different observation types | M1 Scouting |
| A_Greenhouse_Tuta_Registration | ~880 traps × 4 GH | 2024–2025 | Per-trap weekly matrix input | M1 Scouting |
| A_Greenhouse_B_Tabacci_Reg. | ~256 cards × 4 GH | 2024–2025 | Per-card weekly matrix input | M1 Scouting |
| A_Greenhouse_Plant_registration | 1,121 | 2024–2025 | 10+ measurements per plant | M2 Plant Reg |
| A_Greenhouse_Average_fruit_wt | 1,402 | 2024–2025 | Auto-calculation of averages | M3 Fruit Wt |
| FERTILIZER_registration | ~3,500+ | 2019–2025 | 11 compounds, stock tracking | M4 Fertilizer |
| CHEMICAL_REGISTRATION | ~4,000+ | 2018–2025 | 50+ products, 7 seasons | M5 Chemical |
| Average_temp | ~2,500+ | 2022–2025 | 14 readings/day, Inta link | M6 Climate |
| Irrigation | ~8,000+ | 2021–2025 | Complex calculations, dual EVO | M7 Irrigation |

### 4.1.3 Module Architecture (11 Modules)

| Module | Scope | Key Features |
| --- | --- | --- |
| M1 Scouting & Pest | 27 observation types: trap-based (whitefly sticky cards, Tuta delta traps) + section-level (TYLCV, CMV, ToBRFV, Pythium, Botrytis, etc.) + biological (pollination, bumblebees) | Mobile QR scan entry, matrix bulk entry (like Excel), auto-aggregation trap→section, heatmaps, threshold alerts, photo attachments, admin-configurable observation types |
| M2 Plant Registration | 10+ growth measurements per plant: leaves, trusses, fruits, growth/week, leaf length/width, head width, stem diameter, fruit occupation | QR scan plant ID, mobile entry with context, matrix mode (e-gro style), weekly section averages, growth vs target charts, missing data alerts |
| M3 Fruit Weight | Regular sampling: trusses, tomato count, gross/net weight, box type | Auto-calculate: net weight, avg fruit weight. Trend charts per section, row-level comparison, quality grading (small/medium/large), feeds P3 Export harvest data |
| M4 Fertilizer | 11+ compounds daily tracking + stock management (received, consumed, remaining) | Daily matrix entry (compound × day), monthly/season totals, stock balance with low-stock alerts, 6 seasons historical, osmosis chemicals separate, season comparison |
| M5 Chemical (Pesticide) | 50+ products catalog with active ingredients, chemical groups, target pests | Application log (date, product, qty, section, pest), safety interval tracking, year-over-year comparison, target pest analysis, 7 seasons historical |
| M6 Climate & Temp | Per section (7), per part (2), per day: day/night/avg temp + solar radiation | Inta EVO auto-import (background service), color-coded temp display, day vs night differential, weekly summary linked with plant registration + radiation, section comparison |
| M7 Irrigation | 3 measurement points (unit/drip/drain) × 3 params (volume/EC/pH) per section per day | Auto-calculate: drain%, drip/m², uptake, cc/J efficiency. Dual EVO valve mapping, slab weight tracking, EC/pH calibration log, traffic light dashboard |
| M8 Reporting | Main dashboard + standard reports + heatmaps + custom report builder | Season overview, pest summary with trend arrows, growth status, climate snapshot, irrigation status, alert panel. 9 standard report types, heatmap overlays, CSV export |
| M9 Administration | Users, seasons, greenhouse structure, trap locations, catalogs, controller mapping, alert thresholds | 5 user roles, season management, greenhouse/section/row/post setup, trap QR registry, fertilizer/chemical/box catalogs, Inta EVO mapping, configurable thresholds, audit trail |
| M10 Harvest Recording (NEW v3.0) | Daily harvest per section: weight, sort grade, destination (export/domestic/storage), link to P3 shipments, Gapy Satys (domestic sales with 1:10 quota) | Mobile harvest input (PWA, offline), daily harvest dashboard (real-time kg per section), available harvest indicator (7-day forecast), link to P3 export shipments, Gapy Satys tracking with auto 1:10 quota, cumulative season totals, section productivity analytics |
| M11 Weekly Harvest Planning (NEW v3.0) | Weekly planning grid (sections × days), planned kg per section per day, plan vs actual tracking, export demand integration (P3), drag-and-drop rescheduling | Weekly planning grid (Mon–Sat), plan vs actual with color-coded completion, drag-and-drop reschedule with change log, export demand comparison (when P3 connected), week-over-week accuracy, truck capacity alerts, planning history archive |

### 4.1.4 Key Data Entities

| Entity | Key Fields | Volume | Purpose |
| --- | --- | --- | --- |
| Greenhouse/Section | code (A1–A4), area_m2, rows, posts, status | 4 GH, 7 sections | Structure |
| TrapLocation | QR_code, type (sticky/delta), section, row, post, active | ~208 sticky + ~100 delta | QR-scannable traps |
| ScoutingObservation | trap/section, observation_type, date, count/value, photo, scout | ~10,000+/season | Pest monitoring |
| ObservationType | name, category, value_type, trap_level/section_level, threshold | 27+ configurable | Admin catalog |
| PlantMeasurement | plant_QR, date, section, 14 measurements (leaves, trusses, growth, etc.) | ~1,100/season | Growth tracking |
| FruitWeightSample | date, section, QR, trusses, tomatoes, gross_wt, box_wt, net_wt, avg_wt | ~1,400/season | Quality tracking |
| FertilizerApplication | date, compound_id, quantity, season | ~3,500+/season | Nutrition tracking |
| FertilizerStock | compound, received, consumed, remaining, date | ongoing | Inventory |
| ChemicalApplication | date, chemical_id, quantity, section, target_pest, notes | ~4,000+ across 7 seasons | Pesticide log |
| ChemicalCatalog | name, active_ingredient, group, target_pest, unit, dose | 50+ products | Product catalog |
| TemperatureReading | date, section, part, day_temp, night_temp, avg_temp, solar_radiation | ~2,500+/season | Climate data |
| IrrigationReading | date, section, 3 points × 3 params, drain%, drip/m², uptake, cc/J | ~8,000+/season | Water management |
| AlertThreshold | observation_type, metric, warning_level, critical_level | configurable | Automated alerts |
| GreenhouseMap | layout image, section coordinates for heatmap overlay | 1 per greenhouse | Heatmap base |
| HarvestRecord (NEW) | date, section, weight_kg, boxes, sort_grade, destination (export/domestic/storage), shipment_link, inspector, photo, notes | ~2,000/season | Daily harvest output. Feeds P2+P3. |
| WeeklyHarvestPlan (NEW) | week, section, day (Mon–Sat), planned_kg, actual_kg, status, revision_log | ~780/year | Planning grid. Plan vs actual. |

### 4.1.5 User Roles (5 roles)

| Role | Can Do | Cannot Do |
| --- | --- | --- |
| Administrator | Everything: manage users, configure system, enter/edit/delete all data, view all reports | N/A — full access |
| Agronomist | Enter/edit observation data across all modules and sections. View all reports. Manage observation types, fertilizer catalog, chemical catalog. | Cannot manage users or system settings (season dates, greenhouse config) |
| Data Entry | Enter daily readings for assigned modules. View reports for assigned modules. | Cannot edit historical data, no admin access, cannot view unassigned modules |
| Viewer | View all dashboards and reports. Export data as CSV. | Cannot enter or edit any data |
| Block Manager | Enter scouting data and plant measurements for assigned sections only. | No data for other sections, no fertilizer/chemical/irrigation access, no admin |

### 4.1.6 Implementation Phases (Internal to P1)

P1 has 11 internal phases totaling 24–32 weeks (6–8 months):

| Phase | Deliverables | Details | Weeks | Priority |
| --- | --- | --- | --- | --- |
| 1 | Platform Core + Admin | Greenhouse structure setup, user management (5 roles), season management, trap location registry with QR codes, observation type catalog, database schema | 3–4 | CRITICAL |
| 2 | Scouting & Pest (M1) | Trap-based data entry (mobile QR scan + office matrix), 27 observation types, section auto-aggregation, heatmaps, threshold alerts, photo upload | 3–4 | CRITICAL |
| 3 | Plant Reg + Fruit Wt (M2+M3) | Plant QR scan entry, 14 measurements, weekly section averages, fruit weight sampling with auto-calculations, quality grading | 2–3 | HIGH |
| 4 | Fertilizer + Chemical (M4+M5) | Daily fertilizer matrix entry, 11+ compounds, stock management, chemical catalog (50+ products), application log, safety intervals | 3–4 | HIGH |
| 5 | Climate + Irrigation (M6+M7) | Temperature entry (or Inta auto-import), solar radiation, irrigation 3-point measurement, all auto-calculations (drain%, cc/J), EC/pH calibration log | 3–4 | HIGH |
| 6 | Inta EVO Integration | Background service for auto-importing temperature and irrigation data from EVO-1 and EVO-2 controllers. Valve-to-section mapping. | 2–3 | HIGH |
| 7 | Reporting Dashboard (M8) + Harvest Recording (M10) + Weekly Planning (M11) | Main dashboard, 9 standard reports, heatmap overlays on greenhouse map, cross-module weekly view. NEW in v3.0: Mobile harvest input form (PWA, offline), daily harvest dashboard, available harvest indicator (7-day forecast), link to P3 shipments, Gapy Satys domestic sales + 1:10 quota feed, weekly planning grid (sections × days), plan vs actual tracking, drag-and-drop reschedule, export demand integration. CSV export | 4–6 | MEDIUM |
| 8 | Data Migration | Import all historical data from 9 Excel files (7 seasons). Handle inconsistent date formats, merged cells, varying column structures. Verify totals match. NOTE: Data migration now also covers harvest and planning module seed data. | 2–3 | CRITICAL |
| 9 | Mobile PWA + Polish | Offline-first PWA for greenhouse use, QR scanning optimization, performance testing (<3s load), user training, acceptance testing (17 criteria) | 2–3 | CRITICAL |

With 2 developers: ~7.5 months. With 3 developers: ~5.5 months.

### 4.1.7 Acceptance Criteria Summary

The Greenhouse TechSpec defines 17 acceptance criteria across 4 categories (expanded in v3.0 to cover harvest recording and weekly planning): Data Completeness (all 27 observation types, 1,121 plant records, 1,402 fruit weight records imported with matching totals), Functionality (QR scan entry, matrix mode, heatmaps, all auto-calculations matching Excel formulas, cross-module weekly view), Performance (Windows + Android/iOS, <3s load, 30-min training for Excel-familiar users, offline sync), and Sign-Off (written approval from agronomist team).

## 4.2 PROJECT 2: Fleet Management & International Logistics

EXPANDED SCOPE — Based on Transport TechSpec v1.0 4 Core Modules: Fleet · Drivers · Service & Maintenance · Trips (Logistics) 3 Cross-Cutting: Document Control · Notifications · Roles & Permissions

| Parameter | Value |
| --- | --- |
| Scope | Complete fleet lifecycle: vehicle registry (tractors + trailers) with QR codes, driver personnel with document/visa tracking, maintenance forecasting (mileage-based), tire/oil/battery lifecycle, trip logistics with stoppage logging, per-trip P&L, fuel norm tracking, GPS (Traccar), Power of Attorney generation, dispatcher dashboard |
| Key output | Real-time fleet visibility: WHICH TRUCKS/DRIVERS ARE AVAILABLE? Are documents valid? What’s the trip profit? Where are trucks now? |
| Current state | Excel spreadsheets for trucks/drivers. Phone calls for availability. No document expiry tracking. No trip profitability. No fuel norms. |
| Users | Dispatcher (trip management), Technician (maintenance), HR Manager (driver documents), Management (analytics) — 4 dedicated roles |
| Key integration | Traccar GPS (self-hosted, open source) + Trip Management System (existing Django app) + P3 Export shipment data |
| Estimated duration | 24–32 weeks in 11 internal phases |
| Technical Spec | Full specification available: Transport_TechSpec_v1.0 |

### 4.2.1 Core Problems Solved

| # | Problem | Current State | Target State |
| --- | --- | --- | --- |
| 1 | No fleet visibility | Excel, phone calls | Real-time dashboard with status badges |
| 2 | Document expiry risks | Manual tracking, missed deadlines | Auto-alerts 30/14/5 days + auto departure ban |
| 3 | Border entry bans | Discovered at border | Auto departure ban before trip assignment |
| 4 | Unknown trip profitability | Revenue known, costs scattered | Per-trip P&L with auto-calculation |
| 5 | Fuel manipulation | No tracking | Per-100km norm with flag alerts |
| 6 | Maintenance surprises | Reactive repairs only | Mileage-based predictive forecasts |
| 7 | Driver accountability | Subjective assessment | Data-driven reliability scoring (Reliable/Normal/Risky) |
| 8 | Stoppage losses | No tracking | Log + cost + bottleneck analysis |

### 4.2.2 Module Architecture (4 Core + 3 Cross-Cutting)

| Module | Scope | Key Features |
| --- | --- | --- |
| FLEET | Tractors, Trailers, QR Codes, Status | Brand/model/VIN registry, auto-QR, status transitions (Active/On Trip/In Repair/Departure Ban), mobile QR scan view |
| DRIVERS | Personnel, Documents, Visas, Penalties, Scoring | 9 document types with expiry, multi-country visas, penalty log, automated reliability scoring |
| SERVICE | Mileage, Repairs, Tires, Oil, Batteries, Spare Parts | Maintenance forecasting, tire position tracking, oil change intervals, battery lifecycle, spare parts inventory |
| TRIPS | Orders, Routes, GPS, Stoppages, Finance, POA | Trip wizard with validation, per-trip P&L, fuel tracking with norms, stoppage logging, Traccar GPS, POA auto-generation |

| Cross-Cutting | Key Features |
| --- | --- |
| Document Control | Monitors ALL expiry dates. 30/14/5-day auto-alerts. Auto departure ban on expiry. Auto-unban on renewal. |
| Notifications | Telegram (primary) + WhatsApp + In-app. 10 event types, 4 priority levels. |
| Roles & Permissions | 4 roles: Dispatcher (trips), Technician (service), HR Manager (drivers), Management (all). |

### 4.2.3 Implementation Phases (Internal to P2)

| Phase | Deliverables | Weeks | Priority |
| --- | --- | --- | --- |
| 1 | Core Fleet + Drivers: CRUD, documents, status, QR | 4–5 | CRITICAL |
| 2 | Document Control: expiry tracking, 30/14/5 alerts, auto ban, Telegram | 2–3 | CRITICAL |
| 3 | Trips Core: CRUD, validation (ban + visa checks), wizard | 3–4 | CRITICAL |
| 4 | Trip Finance + Fuel: revenue/expenses, fuel norms, P&L | 2–3 | HIGH |
| 5 | GPS + Live Map: Traccar integration, route history, speed | 2–3 | HIGH |
| 6 | Service & Maintenance: mileage, forecasts, tire/oil/battery | 3–4 | HIGH |
| 7 | Stoppages + Penalties + Scoring: logs, fines, driver scoring algorithm | 2–3 | MEDIUM |
| 8 | Dashboards + Reports: dispatcher dashboard, executive analytics, POA gen | 2–3 | MEDIUM |
| 9 | Polish + Deploy: spare parts, mobile PWA, testing, migration, training | 2–3 | MEDIUM |

## 4.3 PROJECT 3: Export Operations

Yük Lifecycle (13 ädim) → 9 Roles → Kanban → Quota → Planning — HIGHEST PRIORITY, START HERE

| Parameter | Value |
| --- | --- |
| Scope | Complete shipment lifecycle: 13 steps, 9 roles, 44 data fields per shipment. Kanban tracking, quota management, weekly planning. |
| Key output | SINGLE SOURCE OF TRUTH for all export operations. Replaces the main 983-row Excel. |
| Current state | Excel with 983 rows, 44 columns. 9 roles edit same file. 90 reports missing. |
| Users | ALL 9 roles: Gadam, Agamyrat, Soltanmyrat, Sirin, Aynur, Malik, Haltac, Arap, Aganazar |
| Prototype | 14-screen interactive HTML prototype with real data ALREADY BUILT |
| Estimated duration | 10 weeks (Phase 1 in roadmap — START HERE) |
| Dependencies | None — Excel data available. All downstream projects depend on this. |

### The 13-Step Shipment Lifecycle

| # | Step | Action | Who | Platform Feature |
| --- | --- | --- | --- | --- |
| 1 | Yüklenme | Load truck at block | Sklad | Mobile form + weight |
| 2 | Gümrük girish | Submit to TM customs | Sirin | Document auto-gen |
| 3 | Gümrük chykysh | Customs approved | Sirin | Status auto-update |
| 4 | Yola chykdy | Truck departs | Transport | GPS tracking starts |
| 5 | Serhet TM | At TM border | Driver | Geofence alert |
| 6 | Serhet gechdi | Crossed border | Driver | Auto-status update |
| 7 | Dest customs | Cleared dest customs | Broker | Status update |
| 8 | Yolda | In transit | GPS | Live map tracking |
| 9 | Bardy | Arrived at city | Sales rep | Notification |
| 10 | Satylär | Being sold | Sales rep | Status update |
| 11 | Satyldy | Fully sold | Sales rep | Price + weight confirmed |
| 12 | Hasabat | Report submitted | Sales rep | MANDATORY form |
| 13 | Tamamlandy | Payments received | Accounting | Auto-close |

Key Business Rules: Standard truck = 18,100 kg net / 20,500 kg gross. Shipment code = DDMM+seq/YY. 9 roles with field-level permissions. 13:00 deadline. Multi-firm split (2 or 3 firms). Gapy Satys = domestic sale (1:10 quota). Missing reports blocked.

Key Screens (14): Dashboard · Shipment List · Shipment Detail · New Shipment · Tracking Board (Kanban) · Customers · Quota Dashboard · Weekly Planning · Finance · Contracts · Documents · Reports · Settings

## 4.4 PROJECT 4: Contracts, Sales & Documents

28 Contracts → 461 Invoices → $10K Rule → 8 Doc Types → Auto-Generate

| Parameter | Value |
| --- | --- |
| Scope | Contract registry, invoice tracking, $10K warning, 8 document template auto-generation, PasportSdelki, debt monitoring |
| Key output | VISIBILITY into $8.3M outstanding debt + AUTO-GENERATION of 8 document types + $10K compliance |
| Current state | 23-sheet Excel with contracts, invoices, templates. Manual fill 2–3 hours/day. |
| Estimated duration | 8 weeks (Phase 2 in roadmap, after P3 Export core) |
| Dependencies | P3 Export for shipment data. Invoices link to shipments. |

### Document Auto-Generation (8 Templates)

| Template | Purpose | Auto-fill From |
| --- | --- | --- |
| CMR (RU/EN) | Road transport waybill | Shipment + seller + buyer + route |
| CMR (3 firms) | Rare: 3-way split | 3 firm splits on 1 truck |
| Invoice (RU/EN) | Commercial invoice | Contract + weight + price |
| TIR Carnet | Transit for Uzbekistan | Route + truck + customs |
| Customs Declaration | Gümrük beyäny | Full shipment data |
| Fito Certificate | Phytosanitary | Product + origin |
| CT-1 Certificate | Certificate of Origin | Origin data |

## 4.5 PROJECT 5: Finance & Executive Dashboard

Töleg → Kredit → Logo Tiger → 1C → Unified Dashboard

| Parameter | Value |
| --- | --- |
| Scope | Payment tracking, credit monitoring per firm, route profitability, Logo Tiger ERP + 1C integration, executive dashboard |
| Key output | SINGLE DASHBOARD: revenue, debt, profit by route, firm risk scores, credit health, greenhouse yield economics |
| Estimated duration | 10 weeks (Phase 6 in roadmap, needs P3+P4+P2 data) |
| Dependencies | P3 Export + P4 Contracts + P2 Trip financials + P1 Greenhouse yield data |

### Executive Dashboard Widgets

| Widget | Shows | Data Source |
| --- | --- | --- |
| Revenue KPIs | Total YTD, monthly trend, vs last season | P3 + P4 |
| Outstanding Debt | $8.3M breakdown by firm, aging analysis | P4 Contracts |
| Credit Health | Per-firm: credit balance vs payment vs inflow | 1C + P4 |
| Route Profitability | Revenue − cost per route, trip-level P&L | P3 + P2 Trips |
| Quota Status | All 24 firms: used/remaining, 1:10 visualization | P3 + P1 |
| Greenhouse Yield | Fruit weight trends, harvest forecast, pest pressure summary | P1 Greenhouse |
| Fleet Operations | Trucks today, departure bans, maintenance due | P2 Fleet |
| Firm Risk Matrix | Debt + credit + quota = risk score | All projects |

# 5. IMPLEMENTATION ROADMAP

## 5.1 Phase Plan (18–24 Months)

Build order optimized for: maximum business impact first, dependency resolution, and incremental delivery. Timeline extended from 12 months (v1.0) to 18–24 months to accommodate expanded P1 Greenhouse (24–32 weeks, 11 modules) and P2 Transport (20–26 weeks, 4 modules).

KEY CHANGES FROM v1.0: P1 Greenhouse expanded from 12 weeks (basic harvest tracking) to 24–32 weeks (11 modules replacing 9 Excel files, 20K+ records, Inta EVO integration, harvest recording, weekly harvest planning). P2 Transport expanded from 12 weeks (truck registry + GPS) to 20–26 weeks (4 modules: Fleet, Drivers, Service, Trips). P1 and P2 development runs in parallel during months 5–16.

| Phase | Months | Deliverable | Project | Team | Impact |
| --- | --- | --- | --- | --- | --- |
| α1 | 1–2 | Export Core — Shipment CRUD, 13-step lifecycle, kanban, import 983 shipments | P3 | 2 dev | CRITICAL |
| α2 | 3–4 | Contracts Core — 28 contracts, 461 invoices, $10K warning, debt dashboard | P4 | 2 dev | CRITICAL |
| α3 | 4–5 | Document Engine — Auto-generate 8 document types, 13:00 deadline, queue | P4 | 1 dev | HIGH |
| α4 | 5–6 | Quota + Reporting — 1:10 ratio system, mandatory sales reports, missing report alerts | P3+P4 | 1 dev | HIGH |
| α5 | 5–10 | Fleet Management Core — Tractor/Trailer CRUD + QR, Driver profiles + documents, Document Control (auto-alerts + departure bans), Trip CRUD + wizard | P2 (Ph 1–3) | 2 dev | CRITICAL |
| α6 | 5–10 | Greenhouse Core — Platform + Admin, Scouting & Pest (M1+M2), Plant Registration + Fruit Weight (M3), mobile PWA with QR scanning | P1 (Ph 1–3) | 2 dev | CRITICAL |
| α7 | 9–14 | Fleet Advanced — Trip Finance + Fuel, Traccar GPS + Live Map, Service & Maintenance, Stoppages + Penalties + Driver Scoring | P2 (Ph 4–7) | 1–2 dev | HIGH |
| α8 | 9–14 | Greenhouse Advanced — Fertilizer + Chemical (M4+M5), Climate + Irrigation + Inta EVO (M6+M7), Reporting Dashboard + Heatmaps (M8), Harvest Recording (M10), Weekly Harvest Planning (M11) | P1 (Ph 4–7) | 1–2 dev | HIGH |
| α9 | 13–16 | Finance Dashboard — Payment tracking, route P&L, greenhouse yield economics, executive widgets, Logo Tiger + 1C integration | P5 | 1–2 dev | HIGH |
| α10 | 15–18 | Data Migration + Polish — P1: import 9 Excel files (7 seasons), verify totals. P2: dispatcher dashboard, spare parts, POA gen | P1+P2 | 2 dev | CRITICAL |
| α11 | 18–22 | Integration + Go-Live — P1 Inta EVO auto-import, mobile PWA optimization, Telegram alerts, cross-project integration, training, parallel run, go-live | All | Full team | CRITICAL |

## 5.2 Visual Timeline

|  | M1–4 | M5–8 | M9–12 | M13–16 | M17–18 | M19–22 |
| --- | --- | --- | --- | --- | --- | --- |
| P3 Export | CORE |  |  |  |  |  |
| P4 Contracts | CORE+DOC |  |  |  |  |  |
| P2 Transport |  | FLEET CORE | ADVANCED | DASH |  |  |
| P1 Greenhouse |  | SCOUT+PLANT | FERT+CLIM | MIGRATE |  |  |
| P5 Finance |  |  |  | CORE |  |  |
| Integration |  |  |  |  | TEST | GO-LIVE |

P3 Export M1–4 · P4 Contracts M1–5 · P2 Transport M5–16 · P1 Greenhouse M5–16 · P5 Finance M13–16 · Go-Live M18–22

## 5.3 Why This Order?

P3 Export first — Most complete analysis (983 shipments); working prototype; core data structure everything depends on; biggest daily pain point; 9 roles interact daily.

P4 Contracts second — $8.3M outstanding debt needs visibility NOW; document auto-generation saves 2–3 hours/day; $10K warning prevents mistakes; builds on P3 data.

P1 + P2 in parallel (months 5–16) — Both have full TechSpecs ready. P1 needs 24–32 weeks (11 modules), P2 needs 20–26 weeks. Running them in parallel with separate dev teams is critical to meeting the 18–24 month timeline. P1 has no dependencies; P2 has soft dependency on P3 (resolved by month 4).

P5 Finance last — Depends on data from all other projects. Richest when P1 greenhouse yields + P2 trip P&L + P3 export + P4 contracts are all feeding data.

# 6. TECHNOLOGY STACK

| Component | Technology |
| --- | --- |
| Backend | Django 5.x + Django REST Framework (Python 3.12) |
| Database | Microsoft SQL Server (MSSQL) — Logo Tiger ERP compatibility. PostgreSQL option for P2 if separate. |
| Frontend | React 18 + Ant Design Pro — enterprise-grade UI components |
| Mobile | Progressive Web App (PWA) for P1 greenhouse (QR scan, offline scouting) + P2 driver fuel/stoppage entry |
| Authentication | Django built-in + JWT tokens. P3: 9 roles field-level. P2: 4 roles module-level. P1: 5 roles section-level. |
| Real-time | Django Channels + WebSocket for live status updates + GPS positions |
| GPS | Traccar Server (self-hosted, open source). REST API. Replaces Navixy/Teltonika plan. |
| Maps | OpenStreetMap or Google Maps + Leaflet.js. Used for P2 live truck map + P1 greenhouse heatmaps. |
| Inta EVO Integration | Background service polling Inta EVO-1 and EVO-2 controllers for temperature + irrigation data. Valve-to-section mapping. |
| Document Gen | python-docx for template filling → LibreOffice/WeasyPrint for PDF. Export docs + POA. |
| QR Codes | qrcode Python library. UUID-based URLs. P2: per vehicle. P1: per trap + per plant. |
| Notifications | python-telegram-bot (primary) + WhatsApp Business API + in-app. P2: 10 event types. P1: pest alerts. |
| File Storage | Local filesystem or S3-compatible (MinIO). Document scans, photos, trap images, receipt photos. |
| Deployment | Docker Compose: Django + React + MSSQL + Redis + Nginx + Traccar (6 services) |
| Development | Claude Code multi-agent: Lead (Opus) + sub-agents (Sonnet) per module |

# 7. TEAM & RESOURCES

| Role | Quantity | Responsibilities | Duration |
| --- | --- | --- | --- |
| Lead Developer | 1 (full-time) | Architecture, code review, integrations (Inta EVO + Traccar + Logo Tiger), deployment | 18–24 months |
| Backend Dev (Export/Contracts) | 1 (full-time) | P3 + P4: Django models, API, business logic, data migration for export operations | 6 months → support |
| Backend Dev (Greenhouse) | 1 (full-time) | P1: 11 modules, Inta EVO integration, 9 Excel file migration scripts, heatmap engine, harvest recording, weekly planning | 14–18 months |
| Backend Dev (Transport) | 1 (full-time) | P2: 4 modules, Traccar GPS, document control engine, driver scoring algorithm | 12–16 months |
| Frontend Developer | 1 (full-time) | React UI, Ant Design, charts, Leaflet.js maps, heatmap overlays, mobile PWA (P1 + P2) | 16 months |
| Data Analyst | 1 (existing) | Requirements, testing, user training, stakeholder management, acceptance testing | 18–24 months |
| QA / Tester | 0.5 (part-time) | Testing each phase, regression, UAT coordination | 14 months |

Updated team assessment (v4.0): Minimum viable team: 4 developers + 1 analyst (increased from 3+1 to support parallel P1 + P2 development). Optimal: 5 developers + 1 analyst + 0.5 QA. AI-assisted development: Using Claude Code with multi-agent orchestration can accelerate development by 30–50%, effectively making a 4-person team perform like 5–6. Critical parallel streams: Months 5–16 require 2 separate backend developers for P1 and P2 running simultaneously. The Lead Developer oversees both and handles integrations.

# 8. RISKS & MITIGATION

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| User resistance — staff comfortable with Excel | HIGH | HIGH | Show prototype early. Train hands-on. Parallel run for 1 month. P1: agronomist sign-off required. | Data Analyst |
| Scope creep | HIGH | MEDIUM | Strict phase boundaries. Backlog for future. MVP first. | Lead Dev |
| P1 + P2 parallel complexity — 2 major projects running simultaneously | HIGH | HIGH | Separate dev teams with clear boundaries. Lead Developer coordinates. Weekly cross-team sync. Shared database schema agreed upfront. | Lead Dev |
| Inta EVO integration — controller API unknown | MEDIUM | HIGH | Phase 6 in P1 dedicated to integration. Fallback: manual entry continues. Study controller API early in month 5. Not a blocker for other P1 modules. | Lead Dev |
| Data migration (9 Excel files) — 7 seasons, inconsistent formats | HIGH | HIGH | Dedicated phase (P1 Ph 8). Handle date format variations, merged cells, text-as-numbers. Verify totals match Excel. Start migration scripts early. | Backend Dev |
| Developer hiring — now need 4–5 devs | HIGH | HIGH | Remote developers (CIS region). P1 dev needs agronomist/greenhouse domain understanding. AI-assisted development to reduce team size. | Management |
| Season timing — extended to 18–24 months vs Sep 2026 | HIGH | HIGH | P3 Export MVP by month 4. P1 scouting module by month 10 (before peak pest season). P2 fleet core by month 10. Full system by early 2028. | Lead Dev |
| MSSQL limitations | MEDIUM | MEDIUM | Known constraints documented. Workarounds identified. | Lead Dev |
| 1C integration complexity | MEDIUM | LOW | Manual import first. Study API later. | Data Analyst |
| P1 offline/mobile complexity — PWA in greenhouses with poor internet | MEDIUM | MEDIUM | Service worker + IndexedDB for offline. Sync on WiFi. Test extensively in actual greenhouse conditions. | Frontend Dev |
| P1 heatmap rendering — greenhouse map overlay with real-time data | LOW | MEDIUM | Use Leaflet.js or D3.js for heatmap. Greenhouse map uploaded as image. Section coordinates mapped in admin. | Frontend Dev |

# 9. SUCCESS METRICS & KPIs

| KPI | Current Baseline | 6-Month Target | 12-Month Target | 18-Month Target |
| --- | --- | --- | --- | --- |
| Shipments in platform | 0 (all in Excel) | 100% new shipments | 100% + historical | Full operational |
| Missing sales reports | 90 (19.5%) | < 10 (< 2%) | 0 (enforced) | 0 |
| Document prep time | 2–3 hours/day | 1 hour/day | 30 min/day | 30 min/day |
| Greenhouse Excel files replaced | 0 of 9 | N/A (P1 starting) | 3 of 9 (scouting + plant + fruit wt) | 9 of 9 (all modules live) |
| Greenhouse data entry method | Paper → Excel | N/A | Mobile QR entry for scouting | Full mobile PWA for all modules |
| Pest alerts (auto) | 0 (manual Excel review) | N/A | Scouting alerts active | Full threshold system + heatmaps |
| Inta EVO integration | Manual copy | N/A | API studied | Auto-import active |
| Historical data migrated | 0 seasons | N/A | Current season | All 7 seasons (2018–2025) |
| Fleet visibility | 0% (Excel) | N/A | Core fleet + drivers online | Full fleet + GPS + maintenance |
| Border incidents | Unknown | N/A | Zero (auto ban) | Zero |
| Trip profitability | 0% tracked | N/A | P&L for new trips | Full route analysis |
| User adoption (all roles) | 0% | 70% (export roles) | 85% (+ GH + transport) | 100% (all roles) |
| Executive self-service | 0% | 50% (partial) | 80% | 95% (full dashboard) |

# 10. IMMEDIATE NEXT STEPS

The following actions should be taken within the next 30 days to begin execution:

| # | Action | Details | Deadline | Owner |
| --- | --- | --- | --- | --- |
| 1 | Management presentation | Present Roadmap v4.0 to directors. Highlight expanded P1 + P2 scope, 18–24 month timeline, 4–5 developer requirement. | Week 1 | Data Analyst |
| 2 | Prototype demo | Show 14-screen P3 prototype to Gadam, Sirin, Arap. Collect feedback. | Week 1–2 | Data Analyst |
| 3 | Greenhouse TechSpec review | Review Greenhouse TechSpec v3.0 with agronomist team at Yigit ES. Validate 11 modules, answer discovery questions for M10 Harvest + M11 Planning, confirm acceptance criteria. Confirm Inta EVO access. | Week 2–3 | Data Analyst |
| 4 | Transport TechSpec review | Review Transport TechSpec v1.0 with Malik, Haltac, dispatcher candidates. | Week 2–3 | Data Analyst |
| 5 | Developer recruitment | Hire/contract 3–4 developers (Django + React). 1 dev needs greenhouse/agri domain. 1 dev needs fleet/logistics. Consider remote CIS developers. | Week 2–4 | Management |
| 6 | Infrastructure setup | Install MSSQL + Traccar. Create YGT database. Test Logo Tiger connection. Research Inta EVO controller API. | Week 2–3 | IT / Dev |
| 7 | Dev environment | Docker Compose scaffold (6 services). CI/CD. First migration. | Week 3–4 | Lead Dev |
| 8 | P3 Sprint 1 kickoff | Start Export Operations: Shipment model + API + list page. Import 983 rows. | Week 4 | Dev Team |

## 10.1 Deliverables Already Completed

| Deliverable | Description | Status |
| --- | --- | --- |
| YGT_Architecture_v2.md | Full technical architecture: 10 Django apps, models, APIs | ✅ Complete |
| YGT_Platform_Prototype.html | 14-screen interactive prototype with real data | ✅ Complete |
| YGT_Business_Process_Map.html | Visual BPM: roles, flows, $10K rule, money flow | ✅ Complete |
| YGT_Discovery_Guide.html | Interview kit for 9 roles + automation matrix | ✅ Complete |
| YGT_Contracts_Analysis.md | Excel analysis: 28 contracts, $8.3M debt | ✅ Complete |
| YGT_UI_UX_Design.html | Production-quality UI/UX with 12 screens | ✅ Complete |
| Transport_TechSpec_v1.0 | P2: 4 modules, data models, 9 phases, API endpoints | ✅ Complete |
| Yigit_ES_Greenhouse_TechSpec_v3.0 | P1: 11 modules (added M10 Harvest Recording + M11 Weekly Planning), 27 observation types, 17 acceptance criteria, 9 Excel file migration plan | ✅ Complete (NEW) |
| CLAUDE.md | Multi-agent orchestration context file | ✅ Complete |
| ygt-platform-scaffold | Docker + Django + React project scaffold | ✅ Complete |
| This Roadmap (v4.0) | Full digital transformation plan with 5 projects, expanded P1 + P2, 18–24 month timeline | ✅ Complete |

# 11. COST & TIME ESTIMATION

This section provides realistic time and cost estimates for two development scenarios: (A) Jasurbek (Data Analyst, Full stack developer) working with AI tools (Claude Code), and (B) Jasurbek + 1 Remote Developer + AI + Outsource IT Company. Server/VPS costs are excluded — the company already has its own infrastructure. Costs are compared at CIS remote and Turkmenistan rates.

## 11.1 Development Effort per Project

Effort is measured in developer-weeks — the total amount of work regardless of team size. Calendar time depends on how many developers work in parallel.

| Project | Modules / Complexity | Total Effort (dev-weeks) | Jasurbek + AI (calendar) | Jasurbek + 1 Dev + Outsource (calendar) |
| --- | --- | --- | --- | --- |
| P3 Export | 13-step lifecycle, 9 roles, kanban, quota, 14 screens. Prototype exists. | 20–26 | 14–18 weeks | 7–9 weeks |
| P4 Contracts | 28 contracts, 461 invoices, $10K system, 8 document templates auto-gen | 17–22 | 11–14 weeks | 6–7 weeks |
| P1 Greenhouse | 11 modules, 27 obs types, QR scanning, heatmaps, Inta EVO, offline PWA, 9 Excel migration (7 seasons), harvest recording, weekly planning | 52–68 | 36–48 weeks | 18–23 weeks |
| P2 Transport | 4 modules + 3 cross-cutting, Traccar GPS, document control, driver scoring, 24 screens | 40–52 | 28–37 weeks | 14–18 weeks |
| P5 Finance | Payment tracking, Logo Tiger + 1C integration, executive dashboard, route P&L | 20–26 | 14–18 weeks | 7–9 weeks |
| Integration + Go-Live | Cross-project integration, testing, data migration verification, training, parallel run | 12–16 | 8–11 weeks | 4–6 weeks |
| TOTAL | All 5 projects + integration | 160–208 dev-weeks | 112–146 weeks (26–34 months) | 56–72 weeks (13–17 months) |

TechSpec v3.0